The "Ryan" model summer program 2026

💥 *The "Ryan" model is envisioned as a six-week Sudanese-style summer program for 2026, with an estimated cost of £1,225 in Europe; it could potentially be developed to operate under a broader annual framework.*

Sudan Connect Café – Summer Programme ٢٠٢٦

*Organizer:*

Sudanese Community in Oxford

*Duration:*

Friday, July 24 – Friday, September 4, 2026

*Target Group:*

Sudanese youth aged 15–30

*Vision*

To cultivate a Sudanese youth community in Oxford that provides a safe space for global connection and learning, fosters a sense of belonging through voluntary summer activities, and prepares future youth leaders within the community.

*Program Objectives*

1- Fostering connections among Sudanese youth in Oxford.

2- Utilizing the summer break for educational, cultural, and recreational activities.

3- Discovering and developing talents and skills.

4- Encouraging volunteer work and community engagement.

5- Establishing an active youth committee to lead future programs.

*Venue*

Weekly activities: The Sudanese Community headquarters at

141–145 Cowley Road,

The Community Hub

This venue accommodates approximately 40 participants and offers an atmosphere well-suited for youth gatherings.

*Closing Ceremony*

Rose Hill Community Centre

Features a spacious hall and a kitchen, making it suitable for the annual celebration and the honoring of students and graduates.

*Weekly Program*

1- Friday, July 24, 2026

*   Opening Gathering – Introductions and Kick-off

*   Participant introductions.

*   Presentation of program objectives.

*   Registration of participants and volunteers.

*   Formation of the Youth Committee.

*   Interactive games and Sudanese hospitality.

*Friday, July 31*

Sudanese Games Night

*   Group games.

*   Cultural competitions.

*   Board games and traditional games.

*   Token prizes.

*Friday, August 7*

*   Creativity and Arts Night

*   Photography and content creation.

*   Arabic calligraphy.

*   Guest appearance by a Sudanese artist or creative.

*Friday, August 14*

* Careers and Leadership Forum

* Meeting with Sudanese professionals.

* CV writing.

* Interview skills.

* Artificial Intelligence: Education and work.

* Entrepreneurship.

*Friday, August 21*

* Culture and Cinema Night

* Screening of a Sudanese film or documentary.

* Open discussion session.

* Sudanese coffee and tea.

*Friday, August 28*

* Community Day

* Group activities and games.

* Workshop on volunteering.

* Program evaluation and preparation for the closing ceremony.

*Friday, September 4*

Sudanese Success Gala

Rose Hill Community Centre

Featuring:

*   Honoring GCSE and A-Level students.

*   Honoring university and college graduates.

*   Honoring outstanding volunteers and youth.

*   Artistic and cultural performances.

*   Guest appearance by a Sudanese artist.

*   Sudanese dinner.

*   Presentation of certificates of appreciation and group photos.

*Supervision and Execution*

The program is overseen by the Executive Committee of the Sudanese Community in Oxford, in collaboration with the Youth Committee, with responsibilities distributed as follows:

General Supervision: Executive Committee.

Program Management: Youth Committee.

Media and Communication: Media Team.

Organization and Reception: Volunteer Team.

Hospitality: Services Team.

Documentation: Youth volunteers.

*Action Plan*

**First: Preparation Phase**

Approval of the program and budget.

Formation of the Youth Committee.

Opening registration for participants.

Launching a social media campaign.

Preparing the community center venue and securing sponsors.

**Second: Implementation Phase**

Holding weekly meetings every Friday.

Documenting activities via photos and video.

Conducting an evaluation meeting after each event.

Monitoring youth participation and encouraging volunteering.

**Third: Evaluation Phase**

Conducting a survey to measure participant satisfaction.

Preparing administrative and financial reports.

*Submitting recommendations for launching a permanent youth program during the academic year.*

*Estimated Budget*

Cost (GBP)

* Hospitality for six meetings	150

* Activity materials	75

* Prizes and certificates	100

* Publicity and design	0 (handled by community volunteers)

* Photography and documentation	0 (by volunteers)

Costs (in GBP for 6 weeks )

*   Hospitality for six sessions: 150

*   Activity materials: 75

*   Prizes and certificates: 100

*   Publicity and design: 0 (handled by community volunteers)

*   Photography and documentation: 0 (by volunteers)

*   Hosting a Sudanese artist: 500 (in coordination with the Oxford House of Music)

*   Rose Hill Community Centre hall rental: 100

*   Closing ceremony dinner contributions: 200

*   Contingency reserve: 100

*   Total estimated budget: £1,225

Funding Sources

Sudanese community contributions.

Donations from businesspeople.

Sponsorship from local institutions and companies.

Small grants from organizations supporting community activities.

In-kind contributions from volunteers and community members.

*Expected Outcomes*

Participation of at least 50–60 young men and women throughout the program.

*   Successful execution of seven diverse events.

*   Establishment of an active youth committee operating under the community's umbrella.

* Discovering and nurturing youth talent.

* Fostering a sense of belonging and a spirit of volunteerism.

* Launching the "Sudanese Success Gala" as an annual event to celebrate the achievements of Sudanese youth in Oxford.

This program represents an investment in the potential of young people and a practical step toward building a generation capable of leading community initiatives. It also strengthens the Sudanese community's presence in Oxford as a force supporting education, culture, and social integration.